## Sheet1
Task | Estimation | Remaining | Status | Date | Priority | Assigned to | Week
Develop endpoint for Arduino | 3 hours | 3 hours | Not started | 12.3.2017 | High | Me | 1
Develop endpoint for Arduino | 6 hours | 3 hours | Started | 12.4.2017 | High | Me
Develop endpoint for Arduino | 8 hours | 1 hour | Started | 12.5.2017 | High | Me
Develop endpoint for Arduino | 8 hours | 0 hours | Finished | 12.6.2017 | High | Me
Develop endpoint for client | 3 hours | 3 hours | Not started | 12.3.2017 | High | Me | 1
Develop endpoint for client | 6 hours | 3 hours | Started | 12.4.2017 | High | Me
Develop endpoint for client | 8 hours | 0 hours | Finished | 12.5.2017 | High | Me
Wire Arduino | 24 hours | 24 hours | Not started | 12.3.2017 | Medium | Me | 1
Reearch how to send data from sim808 to the endpoint | 8 hours | 8 hours | Not started | 12.3.2017 | Low | Me | 1
Wire Arduino | 24 hours | 24 hours | Not started | 12.10.2017 | High | Василен | 2
Reearch how to send data from sim808 to the endpoint | 8 hours | 8 hours | Not started | 12.10.2017 | High | Василен | 2
Refactor server database architecture | 24 hours | 24 hours | Not started | 12.10.2017 | High | Me | 2
Refactor server database architecture | 24 hours | 8 hours | Started | 11.10.2017 | High | Me | 2
Refactor server database architecture | 24 hours | 0 hours | Finished | 12.10.2017 | High | Me | 2
Research for popular android libraries and controllers | 8 hours | 8 hours | Not started | 12.10.2017 | Medium | Me | 2